# Asteria Teams Meeting Recap

Portable meeting source for executive presentation practice

Guaranteed classroom fallback
This recap is a synthetic equivalent of permitted Teams meeting data. Use it when a safe real meeting or direct Teams reference is unavailable. Do not combine this fictional Asteria case with real organizational content.

# Meeting details

| Field | Value |
| --- | --- |
| Title | Asteria service recovery executive review |
| Date | 28 September 2026 |
| Purpose | Confirm whether to run a focused service recovery review and record accountable next actions |
| Participant roles | Meeting Chair, Operations, Technology, and Finance |
| Authoritative source | Asteria_Executive_Review_Transcript.vtt |

# Discussion summary

Operations reported that Claim TAT was above the 48-hour SLA from 14 to 17 September and that complaints were highest from 19 to 21 September.

The meeting did not establish that the routing-rule deployment caused either pattern.

Finance would not confirm a financial effect until the required cost inputs are validated.

Technology can inspect the change log and error queue only after the unresolved Security-access dependency is cleared.

# Confirmed decisions

| Transcript time | Confirmed record | Evidence status |
| --- | --- | --- |
| 00:01:17 | Run a seven-day service recovery review focused on the affected claims queue. | Confirmed by Meeting Chair |

# Confirmed actions

| Transcript time | Action | Owner | Due date | Dependency / status |
| --- | --- | --- | --- | --- |
| 00:01:17 | Complete a daily review of the affected claims queue | Operations | 29 Sep to 5 Oct 2026 | Confirmed |
| 00:01:36 | Share the reviewed queue log | Narin / Operations | 5 Oct 2026 | Confirmed |
| 00:02:34 | Provide initial technical findings | Arun / Technology | 30 Sep 2026 | Requires Security access |
| 00:02:34 | Validate cost inputs before estimating financial effect | Finance | To confirm | Completion date not stated |

# Discussion that was not a commitment

| Source time | Statement | How to treat it |
| --- | --- | --- |
| Chat 14:19 | The chair heard support for a seven-day review. | Discussion only until the chair confirmed the decision in the transcript. |
| Chat 14:25 | Operations could own the daily review if agreed. | Conditional offer; use the transcript to confirm the action. |
| 00:00:57 | Technology could inspect logs after access approval. | Dependency remains unresolved; do not imply access was granted. |

# Unresolved dependencies and missing information

Security access approver and approval date: To confirm.

Finance completion date and validated financial effect: To confirm.

Root cause of the KPI pattern: not established by the meeting record.

Any service target beyond the existing 48-hour SLA: not stated.

# Next decision gate

6 October 2026
Leadership reviews the seven-day queue evidence, technical findings, validated cost inputs if available, and unresolved dependencies before deciding the next action.

# Source boundary

Do not infer beyond the record
Unsupported causes, targets, access approvals, dates, and financial effects must not be added. Write To confirm when information is missing, and trace every presentation claim to this recap or the reviewed Asteria workbook and decision brief.